## Overview
HAX Assessment: AtliQ Lead Capture & Follow-up Assistant
Microsoft HAX Toolkit applied to the working prototype · 10 Oct 2026 · Pankaj Mehta, AI Product Manager
How to use this workbook
1. Guidelines tab: one row per HAX guideline. Update Status, Impact, Effort, Owner and Target as the team decides (yellow cells).
2. Failure scenarios tab: cases the assistant must handle, in the style of the HAX Playbook. Add each one to the eval set.
3. Review this workbook at each rollout gate (shadow alpha, closed beta, phased rollout).
Source: Microsoft HAX Toolkit, Guidelines for Human-AI Interaction (Amershi et al., CHI 2019), https://www.microsoft.com/en-us/haxtoolkit/
Guidelines status
Status | Guidelines | Failure scenarios
Done | 15 | 9
Partial | 1 | 3
Gap | 2 | 2
Total | 18 | 14
Added to the prototype for HAX (commit 8db0a0e)
G1/G2: Dashboard introduction card on what the assistant does, never does, and how far to trust it.
G15: 'Was this useful?' on every email draft and Ask AI answer, logged in the action log.
G16: 'Review and confirm' previews every CRM change before saving (rolled-back dry run).
Top gaps to close next
G13 Learn from behaviour: monthly review of edits, discard reasons and feedback to tune prompts (Feb 2027).
G18 Notify about changes: 'What's new' note on the Dashboard with each release (beta).
G2 Show measured accuracy once shadow-mode evals are complete (Jan 2027).

## Guidelines
HAX Guidelines for Human-AI Interaction: AtliQ Lead Capture prototype
Assessed 10 Oct 2026 against the running prototype. Yellow cells are team inputs; Status drives the Overview counts.
# | Stage | Guideline | Applies? | Status | How the prototype meets it (evidence) | Gap / next action | Impact | Effort | Owner | Target
1 | Initially | Make clear what the system can do | Yes | Done | Dashboard introduction card: what it does, what it never does (save without Confirm, contact clients, read excluded items). Can be shown again from Settings. | Repeat the key points in the beta onboarding session. | High | Low | PM | Jan 2027
2 | Initially | Make clear how well the system can do what it can do | Yes | Partial | Introduction says drafts can be wrong; confidence shown per field; unsure drafts marked 'Needs review'. | Show measured accuracy (e.g. 'fields correct 9 times in 10') once shadow-mode evals are run. | High | Low | PM, DS | Jan 2027
3 | During interaction | Time services based on context | Yes | Done | Reminders fall due on the real deadline (proposal +7 days, inactive +14 days, revisit dates); live timers; daily summary. | Add reminders outside the app (email digest) in beta. | Medium | Medium | Eng | Jan 2027
4 | During interaction | Show contextually relevant information | Yes | Done | Clicking a field highlights the source sentence; follow-up cards show the last message and suggested next step. |  | Medium | Low
5 | During interaction | Match relevant social norms | Yes | Done | Email drafts are short, warm and professional, written as the owner; acknowledge delays; no invented promises. | Collect tone feedback through 'Was this useful?'. | Medium | Low | PM | Beta
6 | During interaction | Mitigate social biases | Yes | Done | Sensitive personal data excluded from context; cross-sell uses only the same client's history; masking of bank data. | Monthly sample audit of confirmed records (PRD guardrail). | High | Low | PM, Salesperson | Monthly
7 | When wrong | Support efficient invocation | Yes | Done | One-click Draft reply on Follow-ups, Dashboard and Pipeline; Ask AI in the top bar; Re-run with AI. |  | Medium | Low
8 | When wrong | Support efficient dismissal | Yes | Done | Discard (with optional reason), Dismiss and Snooze on reminders, close the email drawer with Esc. |  | Medium | Low
9 | When wrong | Support efficient correction | Yes | Done | Every field is editable before Confirm; choose a different CRM record or create a new lead. |  | High | Low
10 | When wrong | Scope services when in doubt | Yes | Done | Missing values left empty, never guessed; unquoted values dropped; rules-only mode when the AI is unavailable. |  | High | Low
11 | When wrong | Make clear why the system did what it did | Yes | Done | Every value quotes its source; match reasons and scores shown; email facts listed with quotes; answers cite deals. |  | High | Low
12 | Over time | Remember recent interactions | Yes | Done | Ask AI keeps the last 6 turns of the conversation; deal history is used for drafts and answers. |  | Low | Low
13 | Over time | Learn from user behavior | Yes | Gap | Edits, discards (with reason) and feedback are all logged, but not yet used to improve the assistant. | Monthly review of edits, discard reasons and 'No' feedback; tune prompts and matching rules; track trust metric. | High | Medium | PM, DS | Feb 2027
14 | Over time | Update and adapt cautiously | Yes | Done | Nothing changes in the CRM without the owner's Confirm; prompt changes go through tests (26 automated tests). | Version prompts and compare on the eval set before each change. | High | Low | Eng | Beta
15 | Over time | Encourage granular feedback | Yes | Done | 'Was this useful?' on every email draft and Ask AI answer, with an optional reason; logged as ai_feedback. | Add feedback to individual draft fields if edits alone are not enough signal. | Medium | Low | PM | Beta
16 | Over time | Convey the consequences of user actions | Yes | Done | 'Review and confirm' shows every CRM field before and after, new reminders and notes before saving (dry run). |  | High | Low
17 | Over time | Provide global controls | Yes | Done | Pause-processing switch (kill switch); exclusion rules by email, domain, subject or keyword. |  | High | Low
18 | Over time | Notify users about changes | Yes | Gap | No notice when the assistant's behaviour or prompts change. | Add a 'What's new' note on the Dashboard with each release; log prompt versions. | Medium | Low | PM, Eng | Beta

## Failure scenarios
Failure scenarios (HAX Playbook style)
How the assistant should behave when the input or the AI goes wrong. Add each scenario to the eval set before beta.
# | Area | Scenario | Example | Expected behaviour | Prototype today | Status | Test
1 | Input | One email covers two separate deals with the same client | Acme asks about the report automation and a new data platform | Two drafts, or one draft that names both needs | One update draft for the matched deal; the second need may be missed | Gap | To add to eval set
2 | Input | Forwarded thread where the client is only in the quoted part | Dhaval forwards a client thread to Jay | Treat the quoted client as the contact, not the AtliQ sender | Internal forwards about one client conversation are classified as sales | Partial | To add to eval set
3 | Classification | Personal message that uses sales words | A personal email about a 'proposal' or 'deal' | Skipped as not sales; nothing stored | Classifier plus exclusion rules; skipped items have their content wiped | Partial | To add to eval set
4 | Matching | Company nickname or misspelling | 'Acme Retail' vs 'ACME Retail Group Pvt Ltd' | Match the existing deal and show why | Fuzzy company and email matching with reasons and a score | Done | To add to eval set
5 | Matching | Referral: an existing client introduces a new company | A client refers CityWide as a new lead | New lead for the referred company, not an update to the referrer | Referral guard keeps the referrer's deal untouched | Done | To add to eval set
6 | Extraction | Relative date in an undated note | 'Let's talk next Thursday' in a pasted note | Resolve from the note's date, or leave the date empty | Dates resolved from the conversation date; none earlier than it | Done | To add to eval set
7 | Extraction | Revisit date far in the future | 'Nothing gets signed until the acquisition closes, likely Q2 2026' | Revisit reminder for the start of Q2 2026 | Date detector creates a revisit reminder (Quantia, 1 Apr 2026) | Done | To add to eval set
8 | Privacy | Bank details or a password in an email | 'Our account number is …' | Masked before the AI sees it; never stored | Masking before processing; masked values never reproduced | Done | To add to eval set
9 | Input | Non-English conversation | A client email in Hindi or German | Mark for review; do not guess fields | V1 is English only; not tested | Gap | To add to eval set
10 | Input | Very long thread | A 30-message email chain | Use the newest messages; flag that older ones were cut | Input capped at 6,000 characters; older text may be cut without notice | Partial | To add to eval set
11 | Generation | Email draft states a price or date not in the records | 'As agreed, $40k by 15 August' | Flag the fact as unverified so the owner removes it | Each fact must quote the records; unquoted facts flagged in red | Done | To add to eval set
12 | Generation | Answer relies on a stale CRM note | CRM says 'proposal sent'; a newer email says the client declined | Trust the newest conversation and say the CRM is out of date | Prompt rule: newest dated conversation wins | Done | To add to eval set
13 | Generation | Question about data the CRM does not hold | 'What is FinEdge's annual IT budget?' | Say it is not in the records; never guess | Answers only from the context; says so when missing | Done | To add to eval set
14 | System | AI usage limit reached or provider down | Daily token limit hit during a batch | Queue and retry automatically; plain-language message | Back-off until the limit resets; rules mode if no AI key | Done | To add to eval set